## Tabelle1
Risk | Description | Probability of occurence | Damage | Mitigation strategy | Person in charge | Risk factor
System outages | PHP-API is unavailble | 1% | 9 | Redundant infrastructure | Dominik Schmitt | 0.09
Bad time management | Project exceeds deadline | 8% | 3 | Define exact time plan | Timo Rautenberg | 0.24
Versioning troubles | Get trouble with Git-Repository | 3% | 2 | Read Github tutorials | Alex Bierenstiel | 0.06
Personnel deficits | Team member drops out | 5% | 4 | Adjust time plan | Timo Rautenberg | 0.2
Technical deadlock | Technology change required | 20% | 7 | Searching for alternatives | Dominik Schmitt | 1.4
Inexperience of team members | Most of the members use the technologies for the first time | 60% | 5 | Read documentations and tutorials | ALL | 3.0
Influence of the workload of other lectures | Parallel projects like PIC-Simulator, Web-Engineering, ... | 30% | 7 | Strict Round Robin processing | Timo Rautenberg | 2.1
Bugs | Throwback in time plan through bugs | 50% | 4 | Clean coding | Alexander Bierstiel | 2.0
Miscommunication | Inadequate communication among the members | 5% | 2 | Weekly meetings | Timo Rautenberg | 0.1